## JIRA_Backlog
Issue ID | Issue Type | Title | Description | Story Points | Priority | Assigned To | Sprint | Branch Name | Status
TR-1 | Epic | Project Setup | Initial project setup with Flask and environment configuration | 5 | High | Abhay | Sprint 1 | feature/project-setup | To Do
TR-2 | Story | Frontend UI Design | Design responsive UI with input and output sections | 8 | High | Rahul | Sprint 1 | feature/frontend-ui | To Do
TR-3 | Story | Integrate NLP Model | Integrate Helsinki-NLP opus-mt-en-hi model with backend | 13 | High | Abhay | Sprint 1 | feature/nlp-integration | To Do
TR-4 | Story | Create Translation API | Develop /translate POST endpoint in Flask | 8 | Medium | Sneha | Sprint 1 | feature/translation-api | To Do
TR-5 | Task | Error Handling | Handle empty input and server errors properly | 3 | Medium | Rahul | Sprint 2 | feature/error-handling | To Do
TR-6 | Story | Deployment on Render | Deploy application on Render with gunicorn | 5 | High | Abhay | Sprint 2 | feature/render-deployment | To Do
TR-7 | Task | Create Requirements.txt | Add all dependencies for deployment | 2 | Low | Sneha | Sprint 1 | chore/requirements-file | To Do
TR-8 | Story | UI Enhancement | Improve UI with loading animation and styling | 5 | Medium | Rahul | Sprint 2 | feature/ui-enhancement | To Do
TR-9 | Task | Testing & Validation | Test translation accuracy and API validation | 8 | High | Sneha | Sprint 2 | test/api-testing | To Do
TR-10 | Story | Add Future Enhancements Section | Prepare documentation for future improvements | 3 | Low | Abhay | Sprint 2 | docs/future-enhancements | To Do